## Slide 1: DHIC Testing Approach & Plan May 2018

## Slide 2
Context & Agenda
Context
As part of OASIS R1 program, Datahub InfoCenter (DHIC) implementation team plans to Migrate all of historical and incremental Policy data from legacy Mainframe (ACL and MIS) for CA and GL lines Integrate DHIC solution with PolicyCenter and BillingCenter to get renewal and new business policies’ data into DHIC for CA & GL for Rocky Mountain Region(CO, ID, MT, NM, UT, WY). The scope of the InfoCenter reporting delivery is limited to out of the box (OOTB) reports This document compliments OASIS program QA strategy document to provide specific details on data testing OASIS program QA strategy will be leveraged and referred wherever applicable
Agenda
Data QA Framework DHIC QA Scope Details Scope Definitions Out of Scope Items QA Key Considerations Test Phase Details Testing Timeline and key milestones (WIP) Roles And Responsibilities Test Automation QA Assumptions, Dependencies AND Risks Test Environment Testing Criteria Open Questions Appendix

## Slide 3
Data QA Framework
Staging
ACL & MIS DB
Intermediate Stage
MIS
Legacy Systems
ACL (UNISYS)
Guidewire Suite
DHIC Product
Datahub DBs
InfoCenter DIM & FACT
PolicyCenter
BillingCenter
Cognos Reports
Downstream Feeds
MIS
MVR
EARS
Verisk
Data Flow
Testing Focus Areas
Data Movement2 and Performance Benchmarks/Optimization3
Business and Functional Testing, UI/Data Testing
Not in DHIC Testing Scope1
ETL Transformation Testing | ETL Job Testing | Data Load Testing
Simple Transformation Aggregations Joins Lookup Filter Conditions | Restart Ability Data Completeness Data Integrity Data Standardization Audit, Balance and Control Check | Environment Readiness Initial and Incremental data loads testing Performance benchmark/Optimization
Reports Testing
Business and Functional testing Cognos reports layout Prompts and filters Drill down capabilities Security Testing Reports performance testing
Test Phases
Unit Testing
Sprint
Testing
Performance Testing
Regression Testing
UAT
End-to-End
Testing
Smoke Testing
Every Sprint
1. Loading data from ACL mainframe to SQL databases is not planned to be tested and is assumed to be accurate. Any defects root caused to this area will be analyzed by DHIC team
2. Test automation will be considered for all regression testing efforts across the testing focus areas. The scripts will be implemented based on the tools availability and feasibility of implementation
3. There is no SLA defined for ETL jobs and Reports at this time. Performance Benchmark/SLA’s will be identified after executing the End-to-End ETL flow few times and this activity is planned for Sprint 7 and 8
Every 3 Sprints or more often in later Sprints

## Slide 4
DHIC QA Scope Details – Scope Definitions
Legacy History Data Migration |  | DHIC Integrations
ETL transformation testing, job testing and data load testing for legacy historical data migration for: ACL DB to Intermediate Stage (DataHub_Stage) Intermediate Stage to GW DH (DataHub) tables External replica ACL DB to GW DH tables External replica MIS DB to GW DH tables Premium balancing for legacy data in DataHub Entities for which DHIC extensions are added New entities created in DHIC Regression Testing for: DHIC (DataHub & InfoCenter) entities Business impacted sections for Cognos Reports |  | ETL transformation testing, job testing and data load testing will be performed for new entities and extension to existing entities for: GW PC (PolicyCenter) and BC (BillingCenter) to GW DH DataHub to InfoCenter Regression Testing for: DHIC (DataHub & InfoCenter) entities Business impacted sections for Cognos Reports Validating the data in the flat files (dummy tables) feed to MIS, MVR, EARS and Verisk as per the data specifications
End-to-End Integrated System & Performance Testing |  | 
ETL jobs (Initial and Incremental) will be executed sequentially in testing/E2E environment against larger (production like) volume of data. Below testing will be performed: End-to-End Testing to determine if the all the ETL components can connect and work in an integrated fashion Performance Testing to ensure that ETL jobs must complete in defined SLAs. Testing / Development team will also focus on: Any performance degradation during large volume of data load Ability to restart the jobs from the point of failure with maximum efficiency QA team will generate reports under various load scenarios (Initial & Incremental) to validate: Report layout, filters, high level functionality, drill down and drill through capabilities Performance, scalability and stability of reporting tool (Cognos) Time Advance testing (TAT) focused on validating transactions as part of renewal or other subsequent transactions and billing delinquency to ensures that reports/dashboards work as expected for key business scenarios in a production like controlled environment. Please refer Slide # 26 for more details on TAT |  | 
1
2
3

## Slide 5
DHIC QA Scope Details – Out of Scope Items
Legacy History Data Migration |  | DHIC Integrations
Loading data from ACL mainframe to SQL databases is not planned to be tested and is assumed to be accurate. Any defects root caused to this area will be assigned to EA team |  | Validation of how mainframe or other source systems consume the flat files (example ISS integration/files or GL feeds) is out of DHIC QA scope
End-to-End Integrated System & Performance Testing |  | 
Testing of MIS Finance reports are out of QA scope and it has been discussed and agreed with the Finance and Accounting team Finance and Accounting team would own validating the Finance reports coming out of MIS and any other downstream systems from MIS Operational reports from ACL and Synergy is out of QA scope, however these reports will be validated by owners of each of the reports |  | 
1
2
3

## Slide 6
Legacy historical data migration FLOW
Staging
ACL & MIS DB
Intermediate Stage
MIS
Legacy Systems
ACL (UNISYS)
Guidewire Suite
DHIC Product
Datahub DBs
InfoCenter DIM & FACT
PolicyCenter
BillingCenter
Cognos Reports
Downstream Feeds
MIS
MVR
EARS
Verisk
Data Flow
Testing key considerations
Premium balancing in DH tables against Legacy source system Test scenarios to ensure No loss of data while migrating to GW DH Data archival process in DH and IC for Legacy data Rollback Plan in case of incorrect data loaded into DH after initial or incremental loads
1

## Slide 7
Datahub integrations FLOW
Staging
ACL & MIS DB
Intermediate Stage
MIS
Legacy Systems
ACL (UNISYS)
Guidewire Suite
DHIC Product
Datahub DBs
PolicyCenter
BillingCenter
Downstream Feeds
MIS
MVR
EARS
Verisk
Data Flow
2
InfoCenter DIM & FACT
Cognos Reports
Testing key considerations
Flat file feed validation – Testing team will validate the file name, format, content, size, processing time and delivery method DH Audit table validation – Validate data in audit tables to ensure that no data was lost during migration Extract File / Data archival process in DH and IC for Legacy data using Delphix/GW built-in process Rollback Plan in case of incorrect data loaded into DH after initial or incremental loads. Time advance testing (TAT) environment integration with DH

## Slide 8
End-to-End Integrated System & Performance Testing FLOW
3
Staging
ACL & MIS DB
Intermediate Stage
MIS
Legacy Systems
ACL (UNISYS)
Guidewire Suite
DHIC Product
Datahub DBs
InfoCenter DIM & FACT
PolicyCenter
BillingCenter
Cognos Reports
Downstream Feeds
MIS
MVR
EARS
Verisk
Data Flow
1 In absence of performance testing tool, report load performance testing will be done manually by 4-5 (or more) users
2 QA team will work with DevOps team to monitor Database and Cognos server.
Testing key considerations
E2E environment readiness dependency: Successful initial data load for: Legacy to IC PC & BC to IC Generate reports from IC Smoke Testing on data loaded as part of E2E Golden Count Validation – Validate record count for key dimensions and facts in IC/Reports against source system Sum balancing for identified key fields in reports generated. Delta load scheduling – Delta loads will be scheduled in QA environment and testing team will Key in policies in Policy Center in between subsequent incremental loads. Monitor the loads to ensure data is loaded accurately after each load. ETL load performance for DHIC Initial and Incremental loads Report load performance testing1 with multiple users (4-5) accessing individual report at a point of time Server/Resource Monitoring2 – Monitor Database and Cognos server while generating Critical and heavy reports with multiple users

## Slide 9
Test Phases Details
Test Phases
Unit Testing
Sprint
Testing
Performance Testing
Regression Testing
UAT
End-to-End
Testing
Smoke Testing
Every Sprint
Description | Unit test is carried out by the developers to review their code against the spec, check-in into Central, run the ETL jobs and validate if tables are loaded successfully before handing over to the QA team. | Smoke Testing is required when ever ETL code build is deployed in QA environment to make sure that tables are loaded in QA env. Testing team will perform record count and duplicate checks before testing the entity. | Sprint testing is performed for all the user stories for DHIC. Testing team focusses on ETL Transformation testing, Job testing and Data load testing on data loaded in QA Database. | Beginning in Sprint 6 (July/Aug 2018) | ETL jobs (Initial and Incremental) will be executed in E2E environment against larger volume of data to validate the integration of different ETL components. Both functionality and accuracy of data is major focus. | Regression Testing is performed to ensure that no unintended errors result from modifications to DHIC ETL components and Cognos report. | Performance testing is performed during E2E data load to ensures time required for DHIC initial and incremental job runs within optimal time and defined SLAs. Also, Report generation (with multiple users) must complete within agreed upon SLA | After QA testing is successfully completed, this is a Business/User driven testing that encompasses key business scenarios and reports with the intent of replicating as closely as possible the actual use of the data/ reports in production
Env | Development | QA | QA |  | QA | QA | E2E/Pre-Prod | Pre-Prod
Deliverables | Unit Test Cases Test Results Defects Reports | Smoke Test Cases Test Results Defects Reports | Test Cases Test Results Defects Reports |  | Integration Test Scenarios / Cases Integration Test Results Defects Reports | Regression Test scenarios identify by QA during Sprint testing Test Results Defects Reports | Performance Test scenarios ETL job, ETL load and report execution time log Defects Reports | Business scenarios Business user sign off
Team | Development | Testing | Testing |  | Development /Testing | Testing | Development, Testing, DevOps | Business Users
Every 3 Sprints or more often in later Sprints

## Slide 10
Testing Timeline and key milestones
1
2
3
4
5
6
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12

## Slide 11
Roles And Responsibilities
The following roles will primarily plan and execute the various testing methods and techniques called out in the framework
Role | Responsibilities
QA Lead | Develop DHIC Testing Approach and Plan, Test Summary deliverables Manage testing progress across all ETL components and Reporting Report to project lead and other stakeholders on status Report on test progress logged defects, and keep track of fixes for re-testingCo-ordinate with business SME’s / users to create test data for key business scenarios
QA Tester | Create test scenarios and/or cases Execute test cases Follow the defect management process Create traceability matrix
Business SME’s / Business users | Execute UAT test cases and log results Assist in creating UAT scenarios and/or cases Assist in creating UAT test data requirements Review UAT deliverables Provide priority for defect fixes Provide decisions on requirements and defects Sign off UAT

## Slide 12
Test Automation
Existing test automation capabilities:
Testing Team will write Test Scripts/Stored Procedures to conduct regression testing:
  Record count and Duplicate check as part of Smoke Testing.
  ETL Transformation testing for data movement from Source to Target database.
Case for an automated testing tool:
There are numerous test automation tools available both commercial as well open source. Benefits of test automation tool for DHIC implementation are:
Overnight batch for Regression testing
Continue test execution after a failed scenario
Function UI testing for Cognos reports
Run time log for each test script

## Slide 13
QA Assumptions, Dependencies AND Risks
Assumptions |  | Dependencies
Initial and Incremental data loads from ACL mainframe to SQL databases is validated and tested Source to target mappings and data cleansing/scrubbing requirements are correct Before testing an entity, QA team assumes that there is no open issue with high/critical priority in Issue log Legacy source system Interface with other source systems are tested and verified Primary and compoE2Ee keys are defined for DH entities moved for testing Any change in data specification / ETL code, for entities already tested as part of Sprint testing, will be communicated to the testing team QA team will request Development team to copy flat file feeds to external systems like MIS, MVR, EARS and Verisk into dummy tables in QA environment for data validation |  | Testing environment readiness – Latest DDL is executed before running the ETL jobs in QA environment for each Sprint Latest and Updated data specifications are checked in GitHub Test Case review with Business Analyst and Development lead QA team will co-ordinate with external systems MIS, MVR, EARS and Verisk system to ensure that files are consumed successfully Performance Benchmark / Optimization – Data QA team will work with BA/Development team to identify and validate ETL jobs and reporting SLA’s DevOps – Data team will work with DevOps to monitor Database and Cognos server while: Loading data into DH and IC against larger or production like data Generating OOTB from Cognos with multiple users
Risks | Mitigation Strategy
Critical/High priority data quality issues in source system could potentially impact the data testing timeline | QA lead works closely with BA’s and Development team for any showstoppers to obtain a speedy resolution
Planned/unplanned environment outage could impact the overall timelines and cause significant rework | QA lead works closely with the environment team to coordinate the environment refresh plan and plan/prioritize the test sets so the impact could be minimized
Executing test scripts against full volume of data can cause performance degradation. Applying filters to the test scripts to limit the data, could result in missing specific scenario during testing | QA Team will validate and ensure that critical business scenarios are covered as part of test data to the best of their knowledge
ETL jobs taking longer than expected. The expected SLA is not defined for DataHub project Multiple users trying to access the same report at a time could result in Cognos reports performance degradation | QA lead works closely with the BA’s and development team to ensure that identified SLA is not impacting the business timelines

## Slide 14
TEST Environment
Server Details | Purpose | Ownership
Data QA Staging (Yet to create) | QA Test environment is used for testing: ACL DB to Intermediate Stage (DataHub_Stage) MIS DB to Intermediate Stage (DataHub_Stage) Intermediate Stage to GW DH (DataHub) tables | Data QA Team
DataHub and InfoCenter CR12DHSQLQA01 | QA Test environment is used for testing: External replica ACL DB to GW DH tables External replica MIS DB to GW DH tables Premium balancing for legacy data in DataHub Entities for which DHIC extensions are added New entities created in DHIC | Data QA Team
Cognos QA | Cognos reports will be validated by Data QA team in this server | Data QA Team

## Slide 15
Testing Criteria
Testing Type | Objective | Details
Data QA Testing | Entry Criteria | Requirements are completed (mapping) and business rules for test case preparation Test scenarios/test cases are created, reviewed and approved by the BA’s / Business SME’s and loaded in QAComplete for execution Data is loaded into QA environment and Smoke testing is completed successfully with no showstopper defects and environment is stable enough for testing
 | Exit Criteria | 100% of test cases are executed with 85% or more pass rate and with no showstopper or high priority/severity defects open during iteration phase Iteration 8 and beyond 100% of test cases are executed using full volume of data with no showstopper or high priority/severity defects open for balancing the reports. For the data that doesn’t match, the expectation is to have valid reasoning for non match Defect triage has assessed any back log of open defects
 | Suspension Criteria | Testing can not continue due to showstopper defects or outages
 | Resumption Criteria | Showstopper defects / outage are resolved and code is deployed in to the environment for QA to resume/retest
 | Owner | Data QA Team
 | Testing Tools | Manual/Automation

## Slide 16
Open Questions
The following are the meeting minutes from DHIC Test Plan walkthrough, QA Lead will co-ordinate / follow-up with the team for Open Questions
Q # | Feedback | Comments
1 | How business plans to use historical data once it is loaded in InfoCenter ? Who are reporting consumers and actual business users? | We have business user names from PC and BC team. Data QA team will work with business users to understand their expectations
2 | Performance Benchmark / Optimization - ETL data load and Reporting SLA ? | There is no SLA defined for ETL jobs and Reports at this time. Performance Benchmark/SLA’s will be identified after executing the End-to-End ETL flow few times and this activity is planned for Sprint 7 and 8
3 | From program QA perspective when does program plans support DHIC Time Advance Testing? Identify Time Advance Testing Database? | Data QA Team will analyze if QA Time advance environment can be leveraged for data testing, since there will be separate instance of PC and BC for DataHub and InfoCenter, can that environment be used.
4 | Do we currently have any Archival process followed and are there any company wide regulations defined? | [Jane:] Currently there is nothing Achieved/ Purged and data is stored indefinitely QA/Development lead will co-ordinate with Jane / Jay to come up with process on file storage upon archival
5 | What is our approach towards ACL initial load and daily / Incremental feeds | Approach is briefly discussed in test Plan, however QA team will create test cases with detailed test steps on validating Initial and Incremental feeds
6 | Will Performance test for DataHub should be done on different environment or will it be a shared environment? | QA lead will discuss with Rajesh (QA), Michele and Jay to come up with plan on Performance testing environment
7 | When are we planning to integrate DHIC with EDW - Is it at end of Release 1 or Release 1.5? | Jane need to discuss with Jay and PM Rajesh to come up with a plan.
8 | As recommended by Dev Lead, having two QA environments will be helpful in upcoming Sprints | QA team will understand the need of two QA environments and share the plan with the team
9 | Automation feasibility for DHIC testing ? | QA Team will do more analysis on possible automation avenues. QA team will leverage existing automation tools available within UFG
10 | We understand that Scope of MIS Testing is huge, including feed to MIS and downstream validation (reporting is in release 1.5), however data validation in the feed is key and need to be validated | Jane will set up meeting with Don to discuss on the MIS scope Michele need to come up with plan on when Business resources need to be available for testing During meeting, it was mentioned that Joel and Amy Rob can validate MIS downstream and consume / process the data

## Slide 17
appendix
Content
Reference to OASIS Program QA Strategy Data QA Test Strategy Testing Type and Techniques ETL Transformation Testing ETL Jobs Testing Data Load Testing Report Testing Time advance Testing Testing Phases Unit Testing Smoke Testing Sprint Testing End-to-End Testing (E2E) Regression Testing Performance Testing UAT Testing Glossary and Definitions

## Slide 18: DHIC QA Testing Approach and Plan is inline with Program level QA Strategy. Please refer below sections for more details
REFERENCE to OASIS Program QA Strategy
Content | Description | Section #
Risk Based Approach | The QA team is adopting a risk based approach to testing on the program, which means the highest business risks are tested first. This approach helps ensure testing efforts are continually spent on the most critical functionality. | 5.3
Testing Process | For the test phases, either within the iteration testing phase or the stabilization testing phase, the testing process is broken up into three major groupings: Plan, Design, and Execute. Every test phase is planned in terms of the functionality needing testing, the resourcing needs, the available resources, and the expected defect turnover. | 6
Defect Management | This section describe the Defect management process workflow | 7
Risk Management | This section Illustrates the identified QA risks and mitigation for the program | 8
QA Governance | This section highlights: QA tasks across phases OnE2Ee – OffE2Ee daily communication Offshore –Exception handling | 14

## Slide 19
DATA QA Test Strategy
Test Strategy and Approach
Test design strategy / approaches are typically devised at two levels:
  User story based / iteration level test scenarios
  Iteration based test cases are outlined based on the defined user stories. The test scenarios are the driving point for the test cases and each of these test cases can be traced back to their respective user story. The test scenarios are designed in such a way that each scenario defines one or more test case under it(scenarios can be poE2Eive or negative). The scenarios can be grouped based on the functional component that they cover (e.g., field level specification scenarios, triggering condition scenarios).
  The test cases include the detailed step-by-step procedures that help the tester to test a given scenario. The test cases, once designed, are reviewed and any required modifications made. At this point, the test case is considered as ready for execution. The test cases are mapped to individual requirements in order to identify which requirement failed for a particular test case.
  Test cases are prioritized as high, medium, and low in order to prioritize test case execution. The prioritization is done based on the testable condition that it covers and the severity of the user story (based on the functional impact). This prioritization is also helpful with risk based testing.
  QAComplete is the test management tool used to manage and maintain test cases. This tool also serves as a test case repoE2Eory. A traceability matrix is maintained between the testable requirements and test cases to ensure complete coverage.
  End-to-end test scenarios
  Data Team will participate in Program level end-to-end testing and also perform data specific business scenarios, following is the QA approach:
  Data Team will validate key business scenarios/functions with the help of BA’s / Business SMEs.
  Business scenarios could be finance or Non-finance depending on critical business functions.

## Slide 20
Testing Type and Techniques

## Slide 21
ETL Transformation Testing
Transformation testing is carried for the data migration from Legacy source system to DHIC and GW PC & BC to DHIC and other source to implement business requirements and transformation rules
Type of Transformation | Description
Simple transformations | Transformation logic will be used to validate transformation logic against the target table data Example: Change of data type or removal of unwanted spaces from the source
Lookups | Lookup transformation will be used to retrieve value from lookup file or table based on value from the source table. Example: Reference and Conformed Data lookup, Policy state code lookup
Joins | Join transformation will be used to validate condition that matches one or more pairs of columns between the two sources Example: Joining database tables via SQL or look up tables with SAP Data Services transformation
Aggregations | Aggregation transformation used to perform calculation on groups Example: Aggregating policy counts or Written Premium balancing
Filters | Filter transformation validation ensures that only data satisfying the specified filter condition is allowed to pass through. Example: Mapping SQL query filters or transformation logic in data specification. Only records with record type H from Legacy source (Pfile) will flow to DHIC

## Slide 22
ETL Jobs Testing
ETL Job Testing focused on sequential job execution, job dependencies and audit and balance statistics. This testing also validate the restart ability of Jobs during failure and focused on data completeness, data integrity and standardization
Type of Testing | Description
Restart Ability | A process may be aborted from the ETL tool and restarted from the point of failure. The target data would then be validated to ensure that data is not corrupted and integrity is maintained.
Audit, Balancing and Control Checks | Errors would be simulated by introducing exceptions. The data load process would be monitored to confirm if the system handles the errors as per the technical design. The audit data (ETL Log files, Audit tables etc..) will be monitored to ensure that the audit information is captured. For example: ETL_CONTROL table will be populated in case of Premium Balancing failure. Number of records loaded from Legacy into DH
Data Completeness | Validate the source data for primary, duplicate and NULL/BLANK checks. Test whether or not all the data necessary to meet the current and future business information demand are available in the data resource. Data team will work with Business SMEs and BAs to gather key business fields and expected values and verify against the source if all possible values are flowing in the target system.
Data Integrity | Data Integrity testing is performed to ensure that the relationships are valid. Data team will work with Business Analyst to list down the relationships expected in DHIC from Legacy and GW PolicyCenter. Example: Does every policy have a customer account?
Data Standardization | Standardized data elements would be tested to ensure that the data is standard across the DHIC tables. Example: : Does Policy number match a certain format throughout the system ?

## Slide 23
Data Load Testing
ETL construct is tested against initial (one-time) load and subsequent increment loads at a defined frequency. ETL jobs are tested for performance of load or response time during this testing
Type of Load | Description
Initial Load Testing | The initial one-time load helps to identify critical issues with the entire data lineage stream Initial Load Testing should focus on the following: Run DHIC DDL scripts in testing environment to ensure required database tables are empty for successful data load Test for overall load performance including: Time required for complete job run Any performance degradation during data load Ability to restart the data loading from the point of failure
Incremental Load Testing | Capturing changes (Incremental Loading at a defined frequency) is one of the most important functionality of ETL processes Incremental Load Testing should focus on the following: Test for incremental load with non-empty database tables Successful data load including change data capture Test for overall load performance including: Time required for complete job run Overall incremental execution time should be within defined SLAs Ability to restart the data loading from the point of failure
ETL Performance Testing | To validate the performance of data load by running ETL jobs from various source systems like ACL, MIS and Policy Center to DHIC. It also include the time taken to generate files for MIS and other externals sources. Performance Testing should focus on the following: Time required for complete job runs within optimal time and defined SLAs Any performance degradation during large volume of data load Ability to restart the jobs from the point of failure with maximum efficiency

## Slide 24
Report Testing
The Report and analytical testing should focus on core functions such as Data Accuracy, completeness and business user experience.
  GW provides OOTB Cognos reports which will allow business users to analyze and visualize the data. Data team will perform below activities for OOTB reports:
    Business and functional testing– Key business fields will be validated against business rules for subset of test data.
    Security – To validate the different roles and access permissions to the reports
    Performance testing to ensure that OOTB Report execution must complete within agreed upon SLA
  For OOTB re-designed reports, the data QA team will perform additional testing along with testing planned for OOTB with larger volume of data. Following are the additional testing required:
    Business and functional testing ensures that the user experience delivered through Reports is complete and accurate as per the reporting requirement.
    Format Accuracy: Accuracy of format as per report/dashboard requirement.
    User Experience – Ensure ease of usability E.g. Download or Extract report.
Type of Testing | Description
Data Accuracy | There are multiple ways to test data accuracy in a report but the two major methods are: Data validation against source using SQL query – This is the most foolproof method of testing data accuracy and to ensure that the data fetched by the report is in accordance with the requirement Random Sampling – Random sampling is used to test the derived values in a report and is also useful when doing an End to End test on the report. Steps to perform random sampling test: Determine sample size Create sample data Test derived values
Format Accuracy | Accuracy of format is manually checked based on the requirements. In case of drill down and drill through report fields, formats of the values need to be tested at each level For OOTB re-designed reports, test will be performed to validate if Report layout/format adheres to the business requirements/technical design Report formats and report elements will be reviewed to ensure they match with Business Glossary

## Slide 25
Report Testing (contd..)
Reports/Dashboards are tested for performance of load or response time during this testing
Type of Testing | Description
Data Completion | This is mainly tested by SQL query against the source system versus the reports data. Here are the steps: Data Count in Source Vs Target Identify any mismatch
User Experience | User experience testing in Reports ensures the ease of usability, the ease of download/extraction of reports, the ease of filtering etc. (heavily based on requirements) Prompts, filters, drill down and drill through features will be tested by cross referencing information from source system or existing reports (if available) If reports are scheduled, they will be monitored to ensure that the reports run on a scheduled frequency
User Authentication and Security Testing | To test different roles and access permissions to the reports. QA Lead will identify the list of team members involved in Security testing. Validate different types of users and their access to various reports based on permissions defined in requirements. Compatibility of different reports in various formats.
BI Performance Testing | To validate performance, scalability and stability of Cognos under various load scenarios ( Initial and incremental load). Report execution must complete within agreed upon SLA

## Slide 26
Time advance Testing
Time advance testing ensures various components of the dashboards/reports work as expected in a production like environment. Time advance testing is carried out to validate renewal and other subsequent policy transactions and billing delinquency testing
Scope | Approach
Guidewire PolicyCenter and BillingCenter to Reporting | Pre-requiE2Ee: Data Team will validate key business scenarios/functions with the help of Business SMEs/Users from Guidewire PolicyCenter/BillingCenter perspective. This includes finance and non-finance scenarios. Data Team will co-ordinate with PolicyCenter team to key in scenarios identified in above step into PolicyCenter environment Daily Load Audit: To validate business rules and scenarios against the data present in multiple hops after initial and incremental data loads: GW Suite GW DataHub  GW InfoCenter  OOTB Reports Validation Approach: Set up a controlled test environment that would allow evaluation of downstream data deliverables including Data Hub, InfoCenter and associated Reports. Execute DHIC Initial and subsequent Incremental load jobs to load data in InfoCenter Generate OOTB reports after every successful completion of InfoCenter load job Data testing team will help business users to validate the reports

## Slide 27
Testing Phases

## Slide 28: Unit test is carried out by the developers at the time of development with a focus towards business and technology requirements at the unit level
Unit testing
Description |  |  | Responsibility | Support | Environment
Unit testing validates individual ETL job and report to verify that the functionality satisfies the technical design documents. The purpose of unit testing is to verify that every ETL job will execute successfully and achieve the desired results after generating the reports. Both poE2Eive and negative testing would be performed during this phase. The test limits itself to the internal logic of a unit |  |  | Development Team | Data Analyst | Development
Entry / Exit Criteria |  |  |  |  | 
Entry Criteria |  |  | Exit Criteria |  | 
The ETL Job or Report is created Development environment has been successfully installed/configured Test Data is prepared and loaded in to development environment The unit test cases are signed off by Technical Lead |  |  | ETL job executed and unit level source data moved successfully Reports generated and data is populated No Blocker and/or critical defects All test cases and results are available to testing team |  | 
Deliverables and Additional Details |  |  |  |  | 
Deliverables |  |  | Additional Details |  | 
The deliverables are owned by the technology lead Unit Test Cases Unit Test Results + signoff by Tech Lead Defects Reports |  |  | The focus is an individual entity data specification mapping e.g. ETL job migrating policy data from ACL DM to DataHub Unit testing primarily tests the ETL or report functionality rather than data accuracy due to execution in development environment |  | 

## Slide 29: Smoke Testing is carried out when ever the ETL build is deployed to make sure that QA database is ready for further testing
smoke testing
Description |  |  | Responsibility | Support | Environment
Validate the ETL code in QA system prior to accepting for further testing. Basic query like record count, duplicate check would be run after every deployment to verify that the database is available for further testing Provide values for all the prompts and generate the report to validate if data is populated for all the required fields |  |  | Data Testing Team | Data Analyst Development Team | Testing
Entry / Exit Criteria |  |  |  |  | 
Entry Criteria |  |  | Exit Criteria |  | 
Unit Testing is completed QA environment has been successfully installed/configured Test Data is prepared and loaded in to QA environment The Smoke test cases are signed off by Test Lead |  |  | Basic validations are successfully passed Data loaded in QA environment for required DHIC tables Reports generated and data is populated No blockers /Critical defects |  | 
Deliverables and Additional Details |  |  |  |  | 
Deliverables |  |  | Additional Details |  | 
The deliverables are owned by the Testing lead Smoke Test Cases Smoke Test Results + signoff by Test Lead Defects Reports |  |  | Smoke testing, the preliminary level of testing is done to ensure whether the tables are loaded successfully after executing the ETL jobs with latest version from Central |  | 

## Slide 30: Sprint testing emphases on ETL transformation testing, Job testing and data load testing along with dependencies among ETL units
sprint testing
Description |  |  | Responsibility | Support | Environment
Sprint testing is done for all the user stories for DHIC and Reporting that are included in a particular sprint. It will be treated as an integration testing because as the sprint goes on, the new stories will be added and the testing is performed in the same environment. |  |  | QA Test Team | Data Analyst Development Team | Testing
Entry / Exit Criteria |  |  |  |  | 
Entry Criteria |  |  | Exit Criteria |  | 
Test Case signed off by QA Lead Build is deployed in QA environment Smoke Testing is completed No Blockers from earlier sprints which may effect execution of current sprint |  |  | ETL Jobs ran successfully. ETL transformation satisfy the data specification and functional requirements. No Blocker and/or critical defects |  | 
Deliverables and Additional Details |  |  |  |  | 
Deliverables |  |  | Additional Details |  | 
The deliverables are owned by the Testing lead Sprint Test Cases Sprint Test Results + signoff by Test Lead Defects Reports |  |  | Typically the Sprint varies for 4 weeks . After every sprint there will be sprint review meeting which highlights the what went well and what didn’t went well for that particular sprint. |  | 

## Slide 31: The focus of the End-to-End Testing is to test what is covered in the data requirements at an end-to-end level and to validate the integration of the different ETL components
End-to-End Testing (E2E)
Description |  |  | Responsibility | Support | Environment
End-to-End Testing determines if the different ETL components can connect and work in an integrated fashion. This is an end-to-end testing that encompasses all ETL mappings and flat file feeds from source to DHIC and other target system highlighted in QA Framework. E2E for reports focuses on all aspects of reports such as report layout, functionality, filters and drill down/through capabilities. It is always performed under controlled data in terms of volume as well as completeness. |  |  | QA Team | QA Analyst | QA
Entry / Exit Criteria |  |  |  |  | 
Entry Criteria |  |  | Exit Criteria |  | 
End to End test cases are prepared and signed off All ETL components for Legacy and GW PC & BC are integrated Sprint testing is completed for all the entities in scope |  |  | Accurate data is loaded to target entities as per the business rules specified in data requirements No blocker, critical (high or medium) defects All test cases and results are available |  | 
Deliverables and Additional Details |  |  |  |  | 
Deliverables |  |  | Additional Details |  | 
The deliverables are owned by the QA Lead Integration Test Scenarios and/or Cases Integration Test Results + Signoff by QA/project manager Defects Reports |  |  | E2E requires QA environment preparation that may need an initial and incremental load; load time should be accounted in the planning step of testing cycle Typical ETL test cases compare data from source to target entities using SQL queries Both functionality and accuracy of the reports is a major focus |  | 

## Slide 32: Comprehensive Regression testing ensures that the existing entities are working as expected due to DHIC extensions and is carried out once the modification of an entity is built and tested
regression testing
Description |  |  | Responsibility | Support | Environment
Regression Testing is performed to ensure that no unintended errors result from modifications to DHIC ETL components and Cognos report. The results of regression testing are considered as part of the entry / exit and go / no go decisions for each entity and report. |  |  | QA Test Team Development Team | Data Analyst Development Team | Testing
Entry / Exit Criteria |  |  |  |  | 
Entry Criteria |  |  | Exit Criteria |  | 
Data specification is updated and signed off E2E is completed for impacted entities or reports as well as new deployment The impacted regression test cases are identified for execution Build is deployed in QA environment |  |  | No new defects / unintended changes to the code (fixes would be made and regression test cases would be re-run until this occurs) All test cases and results are available |  | 
Deliverables and Additional Details |  |  |  |  | 
Deliverables |  |  | Additional Details |  | 
The deliverables are owned by the Technology lead / Test lead Regression Test Cases Regression Test Results + Signoff by Test lead and/or QA/project manager Defects Reports |  |  | In case of DHIC, regression testing is required whenever there is change (insert new field or update existing field) in data specification document For Reporting, any changes to reporting requirement after E2E will qualify the report for regression testing |  | 

## Slide 33: Performance testing is used to measure several system characteristics, such as ETL Job execution time, load time, resource consumption, and efficiency
Performance testing
Description |  |  | Responsibility | Support | Environment
The Performance Testing determines how the ETL components perform in various load (initial / incremental) scenarios. This will be performed by executing respective ETL job scripts. Performance testing for reports validates execution time, database and Cognos resource consumption while multi users accessing individual report at a time. Performance of ETL and reports should be measured against defined SLAs |  |  | Development Team / QA Team / Infrastructure Team | Development Team Infrastructure Team Data Analyst Business Analyst | QA/E2E
Entry / Exit Criteria |  |  |  |  | 
Entry Criteria |  |  | Exit Criteria |  | 
Sprint and End-to-End Testing is completed Full or larger volume of data populated in the source system Requirements are clearly defined for the expected performance |  |  | Performance tests meets the defined SLAs Performance test results are available |  | 
Deliverables and Additional Details |  |  |  |  | 
Deliverables |  |  | Additional Details |  | 
The deliverables are owned by the Development Team and/or QA Team and or DevOps Team Performance Test Cases/Scripts+ Signoff by QA/project manager Performance Test Results + Signoff by QA/project manager Defects Reports |  |  | Early in the architecture iterations, performance tests are focused on identifying and eliminating architectural-related performance bottlenecks In the construction iterations, the tests help to tune the ETL Jobs and Reports and to verify that the Reports acceptably handle high load Performance testing of data ecosystem needs production (or prod like) data both in terms of quality and volume |  | 

## Slide 34: This is a Business/User driven testing that is performed with the intent of replicating as closely as possible the actual use of the reports from IC and flat file feeds to external system in production
UAT testing
Description | Responsibility | Support | Environment
After the QA testing is successfully completed, the reports are tested by business users. The testing ensures that the acquired data meets the business expectations. The test is carried out with production quality data used in actual business scenarios. At end of this phase, the system should be acceptable to the client for use, in terms of ETL process integrity and business functionality | Business Users | QA Team, Development Team Business Analyst Data Analyst | QA
Entry / Exit Criteria |  |  | 
Entry Criteria | Exit Criteria |  | 
QA Testing is complete with no critical or high defects in OPEN status Defect reports with un-resolved defects have been reviewed by project/program management and Business Users | All UAT cases pass and business signs off on the ETL components and / or Reports |  | 
Deliverables and Additional Details |  |  | 
Deliverables | Additional Details |  | 
The deliverables are owned by the Business Lead Test Summary Report Sign off Business Scenarios Business users sign off | It is critical to define the right group of business user for this test to ensure overall acceptability UAT for data applications will be conducted using scenarios from business users; while the QA team will provide underlying data details |  | 

## Slide 35
Glossary and Definitions
Term | Description
GW | Guidewire
PC | PolicyCenter
BC | BillingCenter
DHIC | DataHub & InfoCenter
QA/QC | Quality Assurance/Quality Control
STLC | Software Testing Lifecycle
ETL | Extract, Transform and Load
BI | Business Intelligence
UAT | User Acceptance Testing
E2E | End-to-End Testing
TAT | Time Advance Testing